# BA Work Plan

PROJECT TITLE: HEALTH LINK 001

Over-all Status:

ON TRACK

AT RISK

ON HOLD

COMPLETE

## DELIVERABLES FOR BA

| Week 0 – Initiation (22 Sep – 25 Sep) | Date & Status |
| --- | --- |
| Task 1: Attend project kick-off meeting | 22nd September, 2026 |
| Task 2: Review Project Mandate: aim, objectives, features, scope and constraints | 23rd September, 2026 |
| Task 3: Record and raise BA queries on scope, requirements and dependencies with the Program Manager | 25th September, 2026 |

| Week 1 – Planning (28 Sep – 2 Oct) | Date & Status |
| --- | --- |
| Task 1: Conduct Gap Analysis (current vs target patient–hospital interaction) | 30th September, 2026 |
| Task 2: Create / finalise Scope Document covering MVP scope, out-of-scope items, assumptions and constraints | 30th September, 2026 |
| Task 3: Facilitate requirements clarification / workshop with relevant stakeholders and SMEs | 1st October, 2026 |
| Task 4: Document High-Level and Low-Level Requirements for the agreed MVP features | 2nd October, 2026 |
| Task 5: Develop and refine User Stories and Acceptance Criteria in line with the requirements | 2nd October, 2026 |
| Task 6: Provide BA input to the RAID Log (PM owns) | 2nd October, 2026 |

| Week 2 – Planning (5 Oct – 9 Oct) | Date & Status |
| --- | --- |
| Task 1: Submit BA Work Plan (Deliverable 1.2.10) | 6th October, 2026 |
| Task 2: Complete SWOT Analysis (Deliverable 1.2.11) | 7th October, 2026 |
| Task 3: Develop Process Maps for key MVP journeys, including account access and contact enquiry | 9th October, 2026 |
| Task 4: Review BA requirements and dependencies against the agreed scope and deliverables | 9th October, 2026 |

| Week 3 – Design (12 Oct – 16 Oct) | Date & Status |
| --- | --- |
| Task 1: Develop Wireframes for agreed MVP journeys/features (Deliverable 1.3.4) | 14th October, 2026 |
| Task 2: Develop Business Model Canvas (Deliverable 1.3.5) | 15th October, 2026 |
| Task 3: Contribute BA requirements and acceptance criteria to the Product Requirements Document (PM/BA) | 15th October, 2026 |
| Task 4: Submit updated BA Work Plan | 16th October, 2026 |
| Task 5: Review design outputs against requirements, scope and user stories | 16th October, 2026 |

| Week 4 – Development Grooming & Planning (19 Oct – 23 Oct) | Date & Status |
| --- | --- |
| Task 1: Confirm requirements are reviewed, prioritised and ready for development/sign-off | 20th October, 2026 |
| Task 2: Align Developer and Tester; hand over approved Requirements, Process Maps and Wireframes | 21st October, 2026 |
| Task 3: Provide Acceptance Criteria and BA input to the Test Plan (Tester/Team owns) | 22nd October, 2026 |
| Task 4: Provide BA input to the UAT Document and ensure requirements/acceptance criteria are traceable (Tester/Team owns) | 22nd October, 2026 |
| Task 5: Review Azure Work Items for traceability to approved requirements and user stories (Team/Developer owns) | 23rd October, 2026 |
| Task 6: Support requirement clarification during development grooming and planning | 23rd October, 2026 |

| Week 5 – Sprint Development (26 Oct – 30 Oct) | Date & Status |
| --- | --- |
| Task 1: Validate requirements with Developer and resolve requirement clarifications | 27th October, 2026 |
| Task 2: Participate in Sprint 1 Planning and confirm the selected work aligns with prioritised requirements | 27th October, 2026 |
| Task 3: Support Tester with Sprint 1 test documents by clarifying Acceptance Criteria (Tester owns) | 29th October, 2026 |
| Task 4: Support the development team with requirement clarification and report material issues to the PM | 30th October, 2026 |

| Week 6 – Sprint Development (2 Nov – 6 Nov) | Date & Status |
| --- | --- |
| Task 1: Attend and support Sprint 1 Demo; review delivered functionality against requirements | 4th November, 2026 |
| Task 2: Support UAT after Sprint 1 Demo by clarifying requirements and Acceptance Criteria (Tester coordinates) | 5th November, 2026 |
| Task 3: Submit updated BA Work Plan | 5th November, 2026 |
| Task 4: Update BA inputs to RAID / Lessons Learnt Log as required | 6th November, 2026 |

| Week 7 – Sprint Development (9 Nov – 13 Nov) | Date & Status |
| --- | --- |
| Task 1: Participate in Sprint 2 Planning and confirm alignment with prioritised requirements | 9th November, 2026 |
| Task 2: Support Tester with Sprint 2 test documents by clarifying Acceptance Criteria (Tester owns) | 11th November, 2026 |
| Task 3: Support development team through Sprint 2 with requirement clarification and traceability | 13th November, 2026 |
| Task 4: Review outstanding requirement issues and confirm readiness for Sprint 2 Demo / UAT | 13th November, 2026 |

| Week 8 – Closure (16 Nov – 20 Nov) | Date & Status |
| --- | --- |
| Task 1: Attend and support Sprint 2 Demo; review delivered functionality against requirements | 17th November, 2026 |
| Task 2: Support final UAT by clarifying requirements and Acceptance Criteria (Tester coordinates) | 18th November, 2026 |
| Task 3: Provide BA input to the End of Project Report (PM owns) | 20th November, 2026 |
| Task 4: Support End of Project Meeting and confirm BA deliverables/requirements records are complete | 20th November, 2026 |

## Project Team

| Role | Name |
| --- | --- |
| Program Manager | Tolu Dada |
| Submitted By | The BAs |
| Team Members | To be confirmed |
| Approved By | To be confirmed |

Why we are doing this? To design and deliver a secure, responsive and user-friendly Hospital Digital Platform MVP that improves how patients interact with the hospital. Patients currently travel, queue or return another day for enquiries and information; this MVP provides online access to account management, hospital information, contact channels and health content. / Delivery: 8 weeks (22 Sep – 20 Nov 2026). Budget: £120,000. Goals: -Deliver the assigned MVP components within 8 weeks and within the £120,000 budget. -Improve communication between patients and the hospital through clear information and accessible support channels. Scope -Customer Account: secure sign-up, sign-in/out, password reset and profile management. -Contact Us: hospital contact details and location, contact form, callback and support channels. -Pharmacy / Medical Products: eligible medical product information, ordering, prescription-status checks, payment where applicable, and collection workflow, subject to confirmed scope/dependencies. -About Us: hospital information, mission, vision and services.