| ## Project Name | ## Project Summary | ## Date Submitted | ## Created By |
| --- | --- | --- | --- |
| HEALTH LINK 001 Hospital Digital Platform (MVP) | Delivery of the MVP components of a secure, responsive and user-friendly Hospital Digital Platform assigned to this project team, covering customer account management, hospital information, communication and enquiry handling, customer support, health-related content, policies and FAQs. Delivery window: 8 weeks. Approved budget: £120,000. | 25/09/2026 | Geraldine Adeniyi, Business Analyst Reviewed by: Tolu Dada Program Manager (PGM) |

Step 1. Project Deliverables (Requirements)

The following deliverables define the committed MPV scope and  their analysis artefacts required to support delivery

| Deliverable | Description |
| --- | --- |
| Customer Account | Secure customer sign-up using a valid email address, including email verification before the account is activated. Sign-in and sign-out functionality with session handling and a secure log-out on inactivity. Self-service password reset via a time-limited, single-use link sent to the registered email address. Creation and ongoing management of a customer profile record. Ability for the customer to view and update permitted personal information (for example name, contact number, address and communication preferences). Fields that must not be self-edited such as clinical identifiers or NHS numbers will be displayed as read-only and flagged during requirements sign-off. Secure account access controls: password complexity rules, failed-login lockout, encryption of credentials at rest and in transit. Supporting artefacts: High-Level Requirements (HLR), Low-Level Requirements (LLR), acceptance criteria, account lifecycle process flow and wireframes. |
| Contact Us | Display of hospital contact information including telephone number(s), email address(es) and physical location. Department-level contact details were provided by hospital SMEs. Online contact/enquiry form with validation of mandatory fields. "Request a call back" option allowing a user to request contact from an authorised hospital representative. Routing of submitted enquiries to the correct hospital contact channel or mailbox based on enquiry category. Automated acknowledgement to the customer and response delivery to the registered or supplied email address. Clear on-screen notice that the form is not to be used for emergencies, with signposting to 999 / NHS 111. Supporting artefacts: HLR, LLR, enquiry-routing matrix, acceptance criteria and wireframes. |
| About Us | General information about the hospital and its background. Display of the organisation's mission statement. Display of the organisation's vision statement. Overview of hospital services and specialisms (informational only — booking is out of scope for this team). Additional organisational information that helps patients understand the hospital, its values and its standards. Content supplied and signed off by hospital SMEs prior to publication. Supporting artefacts: HLR, LLR, content matrix and wireframes. |
| Pharmacy/Medical Products | Enable patients/users to place orders for eligible medical products in accordance with the hospital’s approved eligibility criteria, business rules and MVP requirements. Products that do not meet the approved eligibility criteria will not fall within this ordering capability. Enable patients/users to make payments online where applicable, based on the type of transaction/service and the approved payment requirements for the MVP. Online payment functionality does not imply that every hospital transaction must be payable online. |
| MVP Digital Platform | Deliver the agreed MVP digital platform containing the approved functionalities and requirements within the defined project scope, subject to the project’s assumptions, constraints and approval requirements. |

## Step 2. Out of Scope

The items below are either explicitly excluded by the mandate, allocated to other delivery teams within the wider programme, or excluded by the Business Analyst to remove ambiguity. Items may be reconsidered in a later phase via change control.

| This project will NOT accomplish or include the following: | Out-of-Scope Deliverables/Tasks |
| --- | --- |
| Appointment booking | Online doctor appointment scheduling and booking functionality. |
| Doctor-to-patient matching | Automated matching of patients to an appropriate doctor or specialism. |
| Doctor availability management | Functionality allowing clinicians to set, amend or publish their availability. |
| Management schedule tracking | Visibility of clinician schedules for senior management staff. |
| Pharmacy catalogue and inventory | Online pharmacy catalogue, stock levels and inventory management. |
| Medical product ordering | Placing, confirming and tracking orders for medical products, including collection notifications. |
| Prescription management | Prescription validation, verification and management workflows. |
| Online payments | Payment processing for medicines or medical services, including payment-gateway integration and PCI-DSS scope. |
| Clinical systems integration | Integration with the hospital PAS, EPR, or any clinical record system. No clinical data is created, read or stored by this MVP. |
| Native mobile applications | iOS or Android native apps. Delivery is a responsive web platform only. |
| Telemedicine | Video or audio consultation, remote triage or any form of clinical diagnosis through the platform. |
| Multilingual content | Translation or localisation of platform content into languages other than English. |
| Legacy data migration | Migration of existing patient, contact or content data from legacy hospital systems. |
| Ongoing content authoring | Creation of hospital, health, policy or FAQ copy. The project team builds the capability; the hospital supplies and approves the content. |
| Post-launch BAU support | Ongoing operational support, hosting management and maintenance beyond the agreed warranty/handover period. |

## Step 3. Project Assumptions

Factors considered to be true, real or certain for planning purposes. Each carries a degree of risk; if an assumption proves false, the associated risk will be logged in the risk register and escalated to the Program Manager.

| s/n | Assumption |
| --- | --- |
| 1 | Stakeholders will provide timely feedback, decisions and approvals throughout the project. Requirements sign-off is assumed within 3 working days of submission. |
| 2 | Hospital representatives will supply accurate and complete information on services, contact details, policies, mission, vision and other organisational content by the agreed content-freeze date. |
| 3 | Requirements will remain reasonably stable during MVP development; material changes will follow the agreed change-control process. |
| 4 | Appropriate subject-matter experts will review and approve all health-related information before publication. |
| 5 | The platform will comply with applicable UK data protection, privacy, healthcare, accessibility and regulatory requirements, and the hospital will confirm its own regulatory position where clarification is needed. |
| 6 | Appropriate consent will be obtained wherever customer information is collected, stored or used. |
| 7 | Required hosting, infrastructure, security tooling and technical resources will be available from Week 1 and will not require procurement lead time. |
| 8 | Live chat and customer support will be staffed and managed by authorised hospital personnel; the project team delivers the capability, not the service. |
| 9 | Live chat within this MVP is for customer support and general enquiries only, not clinical diagnosis or emergency medical assistance. |
| 10 | The four out-of-scope functional areas (appointments, pharmacy, prescriptions, payments) are being delivered by other project teams within the wider programme; no dependency on their output is required for this team to go live. |
| 11 | The project team is allocated to this project for the full 8-week duration at the agreed capacity, and team members meet the 75% minimum attendance and participation requirement. |
| 12 | A named Product Owner / Program Manager is available throughout for requirements clarification. |
| 13 | Hospital staff who will administer content, enquiries and live chat will be made available for training before go-live. |
| 14 | UAT participants will be identified and available in the agreed testing window. |
| 15 | Third-party components (email service, live-chat tooling, hosting) are either already licensed or can be procured within budget without extending the timeline. |

## Step 4. Project Constraints

| Project Start Date | Week 1 22/09/2026, to be confirmed at project initiation. |
| --- | --- |
| Launch / Go-Live Date | 2 weeks before the End of Week 8 [06/11/2026]. Go-live is conditional on successful UAT completion and formal stakeholder approval. |
| Project End Date | End of Week 8, following go-live, handover and closure activities. 20/11/2026 |
| Hard deadline(s) | The 8 week delivery window is fixed and stated in the mandate. It is not extendable without Project Sponsor approval. The £120,000 budget ceiling is fixed. UAT must be completed before launch. Formal stakeholder approval must be obtained before release. |
| Key milestones | Week 1 Project initiation, stakeholder identification, scope document approval. Week 2 High-Level Requirements (HLR) elicited and baselined. Week 3 Low-Level Requirements (LLR), wireframes and process models signed off; DPIA started. Week 3 Content freeze: all hospital-supplied content received. Weeks 3–6 Agile development sprints with governance checkpoints at each sprint close. Week 6 System and integration testing complete; SME clinical sign-off on health content. Week 7 User Acceptance Testing and defect resolution. Week 8 Go/no-go decision, deployment, training, handover and project closure. |
| Budget constraints | Total approved budget: £120,000, covering this team's allocated MVP scope only. The budget must absorb resourcing, tooling, hosting, third-party licences and contingency. Any spend that would exceed the ceiling must be escalated to the Program Manager and approved by the Project Sponsor through change control. Costs relating to out-of-scope programme areas are carried by other delivery teams. |
| Quality or performance constraints | WCAG 2.2 Level AA accessibility conformance. Full compliance with UK GDPR and the Data Protection Act 2018; DPIA completed and approved before go-live. Responsive across desktop, tablet and mobile. HTTPS/TLS enforced; protection against OWASP Top 10 vulnerabilities. Target page load under 3 seconds on a standard broadband connection. No health, policy or organisational content published without documented SME approval. Zero open Severity 1 or Severity 2 defects at go-live. Continuous quality assurance applied throughout the lifecycle, not only at the test phase. |
| Equipment / personnel constraints | Delivery is limited to the features allocated to this project team within the mandate. Team capacity is fixed; no additional resource is assumed within the approved budget. Team members must maintain minimum 75% attendance, participation and engagement. Shortfall may result in Almond declining reference requests. Availability of hospital SMEs, legal/information-governance representatives and clinical reviewers is outside the project team's control and is a recognised delivery risk. Live chat cannot go live until hospital support personnel are trained and rostered. Hosting, infrastructure and security tooling must be provisioned by the hospital's technical function. |

## Step 5. Approvals

This scope document requires formal approval from the roles below before requirements elicitation proceeds. Changes to approved scope must follow the agreed change-control process.

| S/N | Role of Approver | Submitted for Approval on: | Approval Received on: |
| --- | --- | --- | --- |
|  | Tolu Dada Program Manager (PGM) | 25/09/2026 |  |

Related Documents

Project Mandate  HEALTH LINK 001

Stakeholder Register and RACI Matrix  to be produced,week 1

High Level Requirements Document to be produced,  week 2

Requirements Traceability  Matrix to be produced,  week 2 onwards

Risk and Issue Log live from week 1

Data Protection Impact Assessment to be produced, week 3-6

Office Use Only: